## Product Backlog
Id | Status | Priority | Size | Partition | Role | Goal | Benefit | Test
8 |  | 3 | L | Documentation | Developer | Enhance the docstring documentation. | Learn how to use reST format to fully document the source. | When I check the generated docs, they mention all args, preconditions, side effects, raised exceptions, return values, and post conditions for each function and method.
12 | Done | 3 | XS | Engine | Developer | Have a World::random_coordinate() method. | Often need to generate random coordinates. | When I call the method, it gives me a random coordinate based on the world size.
16 | Done | 3 | XS | Parser | Player | Ability to say 'north', etc. instead of 'n'. | Easier for player to do what they want in the game. | When I say "north", the hero moves north, etc.
5 |  | 2 | L | Infrastructure | Developer | More unit tests and TDD. | Increase odds of game actually working. Practice this style of development. | When the automated tests run nightly, there is at least 50% code coverage and no failures.
6 |  | 2 | L | Logging | Developer | Conditional debug logging using some framework. | Be able to easily enable logging to debug problems. | When I start the game with some log level, the appropriate amount of debug output occurs.
7 |  | 2 | L | Documentation | Developer | See generated HTML code documentation. | Understand the source at a higher level than rummaging directly through it. | When I go to some URL, the latests code docs have been generated by the nightly build.
13 | Done | 2 | S | Engine | Developer | Make a Death situation. | Centralize death. It's now hardcoded into certain spots. | When hero dies, he transitions to the Death situation.
14 | Done | 2 | S | Engine | Developer | Make a Victory situation. | Centralize victory instead of hardcoding. | When hero wins, the Victory situation can evaluate this and render this correctly.
1 |  | 1 | L | Configuration | Developer | Set global config options in a file. | Less hard-coding in the game engine. | When I set world_size = 5 in config, game runs as 5x5x5.
3 |  | 1 | L | Persistence | Player | Have game resume from saved state. | Don't have to start all over at the beginner. | When I exit and resume game, saved state is restored. I can give a command like 'restart' to restart the game.
4 | Done | 1 | XS | Engine | Player | Restart the game in the game. | Don't have to leave the game to start new session. | When I type 'restart' in CLI, a new game session begins.
9 |  | 1 | XL | Infrastructure | Developer | Host on AWS. | Every company wants AWS experience these days it seems. This would demo that ability. | When I run the game, I can show that it is hosted via AWS somehow.
18 |  | 1 | L | Parser | Dungeon Master | Extend context-specific commands to Entities (as already done for Situations). | Provide significant flexibility in contextual command parsing. | When I have a magic wand, I can say "blast death ball" to destroy it.
19 |  | 1 | S | Engine | Dungeon Master | Gives numbers of charges to things like magic wands. | Allow more interesting game play. | When I use a magic wand, a charge depletes from it.
2 |  | 0 | XXL | GUI | Player | Play game via web interface. | Don't have to mess with GitHub or CLI. | When player goes to some URL, they can play game with zero installation.
10 |  | 0 | M | Content | Dungeon Master | Create a leprechaun that has a lucky charm. The lucky charm allows specific teleportation. | Makes the game more interesting. | When I play the game, I encounter a leprechan that has a lucky charm.
11 |  | 0 | M | Content | Dungeon Master | Let there be ways for rooms/things to have writing on them. | The writing can provide hints as to how to play the game. | When I go into a room, there may be writing in the dust. Each time I visit the same room, it deteriorates further until totally gone.
17 |  | 0 | M | Engine | Dungeon Master | Enforce strength mechanics on inventory weight. | Make the game more interesting/challenging for the player. | When hero tries to pick up item that exceeds carrying capacity, he cannot. Hero cannot move if carrying capacity has been exceeded.
15 |  | -1 | XS | Engine | Developer | Make move_deathballs() just iterate on Entity instance. | Faster. | When I run that method, it does not iterate over every room.
20
21
22
23